## Revision Log
20007
CONFIDENTIAL | [11 empty] | 2021-01-05
44201.818
Revision Log
Project: | CTC
Quotation Summary
DESCRIPTION |  |  | MPL Status | Trades | Date Sent to Trades | RFQ Due Date | Before 5% Markup | Pricing | Date Sent to Owner | Date Approved by Owner | Procore PCO Status | CO# | Trades with Pricing
RN-029 | CR-014 | EHC UV-C Handrail Modules | Approved | Thyssen |  |  | 20280 | 21294 | 2020-11-24 |  | Approved |  | Thyssen
RN-027 | CR-009 | Additional Excavation Inside New Building Footprint | Approved | Tomlinson |  |  | 92014 | 96614.7 | 2020-10-29 |  | Approved |  | Tomlinson
RN-026 | CR-004 | Dynamic Compaction - Tomlinson T+M for Dozer | Approved | Tomlinson |  |  | 4983.7048 | 5232.89 | 2020-10-15 |  | Approved |  | Tomlinson
RN-025 | CR-001 | LL - Grand B - Upfill | Approved | Tomlinson |  |  | 106740.7048 | 112077.74 | 2020-10-15 |  | Approved |  | Tomlinson
RN-023 | CR-011 | CT Tower Crane Banner | Approved | Lundy |  |  | 2107.8095 | 2213.2 | 2020-11-10 |  | Approved |  | Lundy
RN-001 | CR-003 | Menard - Rapid Compaction - Subcontract | Approved | Menard |  |  | 85242 | 89504.1 | 2020-09-23 | 2020-11-04 | Approved |  | Menard
RN-030 | CR-030 | Accommodations for Larger Hoistway | Out for Approval | Thyssen |  |  | 11115 | 11670.75 | 2020-12-18 |  | Pending - In Review |  | Thyssen
RN-005 | CR-010R1 | Removal of Contaminated Water | Out for Approval | Veolia |  |  | 15765.5333 | 16553.81 | 2020-12-23 |  | Pending - In Review |  | Veolia
RN-004 | CCN-004 | Coordination of Existing Mall Condition + Mall Roof Projection | Out for Approval | Tomlinson, Harris, Synergy, Simcon |  |  | 191.8 | 201.39 | 2020-12-22 |  | Pending - In Review |  | Tomlinson, Harris, Synergy, Simcon
RN-002 | CCN-002 | Structural Site Report No. 01 | Out for Approval | Simcon, Harris, Synergy, Tomlinson, Marathon |  |  | 10457.0381 | 10979.89 | 2020-12-22 |  | Pending - In Review |  | Simcon, Harris, Synergy, Tomlinson, Marathon
RN-020 | CR-023 | L2 Slab Pocket Details | Out for Quote | Harris |  |  |  | 0
RN-016 | CCN-006 | Site Conditions at Link of Existing Mall | Out for Quote | Hamilton, Raymond, Synergy, Simcon, Harris, Tomlinson |  |  | 2780 | 2919 |  |  |  |  | Hamilton, Synergy, Simcon
RN-015 | CR-022 | SI-10 Service and Garden Centre Design Changes | Out for Quote | Simcon, Synergy, Integral, Raymond, Harris, LDC |  |  | 5918.25 | 6214.1625 |  |  |  |  | Simcon, Harris
RN-008 | CR-025 | Tie-Beam Relocation | Out for Quote | Harris, Synergy, Tomlinson |  |  | 3826.52 | 4017.846 |  |  | Draft |  | Harris, Synergy
RN-003 | CCN-003R1 | Suit SD Markups, Site Conditions + RFIs | Out for Quote | Thyssen, Synergy, Harris, Simcon, Tomlinson, GA |  |  | 20563.5 | 21591.675 |  |  |  |  | Thyssen, Synergy, Harris, Simcon
RN-022 | CR-015 | SI-009R | Ready to Send to Owner | Synergy |  |  | 6629.75 | 6961.2375 |  |  |  |  | Synergy
RN-021 | CR-019 | SI-01 Added Glazing + Window Frames | Ready to Send to Owner | VPL |  |  | 2268.03 | 2381.4315 |  |  |  |  | VPL
RN-014 | CCN-005 | Suit Escalator Shop Drawings | Ready to Send to Owner | Simcon, Harris, Synergy, Tomlinson, Oconnor |  |  | 1735.75 | 1822.5375 |  |  |  |  | Simcon, Synergy, Oconnor
RN-013 | CR-018 | Shearwall 3Z Re-design | Ready to Send to Owner | Harris, Marathon, Tomlinson, Synergy |  |  | 8719 | 9154.95 |  |  | Draft |  | Harris, Marathon, Tomlinson, Synergy
RN-024 | CR-002 | Temp Dewatering | RFQ not sent | Lundy |  |  |  | 0
RN-019 | CR-031 | RFI-054 Roof Sloping | RFQ not sent | Hamilton, Simcon |  |  |  | 0
RN-018 | CR-032 CR-024 | Bedrock at Glass Elevators + Shearwall | RFQ not sent | Harris, Synergy, Harris, Tomlinson, Marathon |  |  | 3571.15 | 3749.7075
RN-017 | CR-034 | Freight Elevator Slab Thickening | RFQ not sent |  |  |  |  | 0
RN-012 | CR-008 | Lean Mix | RFQ not sent | Lundy |  |  |  | 0
RN-011 | CR-013 | Plan Discrepencies | RFQ not sent | Tomlinson, Synergy, Simcon, Harris |  |  | 22301.27 | 23416.3335
RN-010 | CR-028 | Existing Conditions (mall footings + other areas) | RFQ not sent | Synergy, Tomlinson, Harris |  |  |  | 0
RN-009 | CR-033 | Contaminated Soil | RFQ not sent | Veolia, Tomlinson |  |  | 326.84 | 343.182
RN-007 | CR-029 | Test Pits for Soil Samples | RFQ not sent | Tomlinson |  |  |  | 0
RN-006 | CR-027 | Soil Stock Pile | RFQ not sent | Tomlinson |  |  |  | 0
|  |  |  | Sub Total |  |  |  | 448914.533

## CR-010
RN-005
20007
CONFIDENTIAL | [5 empty] | 2020-12-23
CR-010R1
Project: | CTC
CR-010R1 | Removal of Contaminated Water
Quotation Summary
DESCRIPTION |  | Quantity | Unit | $/Unit | COST | TOTAL
1 | Frac tank delivery and equipment rental |  |  |  | 5101.71 | 5101.71
2 | Mall contaminated water waste removal |  |  |  | 10663.82 | 10663.82
3
4
5
6
7
SUBTOTAL | [5 empty] | 15765.53
| Lundy's Mark-up 5% |  |  |  |  | 788.2765
TOTAL | [5 empty] | 16553.8065
Lundy Concrete Quotation Breakdown
DESCRIPTION |  | Quantity | Unit | $/Unit | COST | TOTAL
1 |  |  |  |  | 0 | 0
2
3
4
5
6
7
TOTAL | [5 empty] | 0
There will be no change in the presently approved contract completion date due to this change
in the work; all costs to maintain this date are included in this CCO.
There will be a change to the present contract completion date of TBD days,
due to the changes in the work.
There may be a revision to the presently approved contract completion date; due to the changes
in the work. MPL reserves the right to assess the actual effects to the original completion date
at a later date due to the impact of this additional work.

## CCN-004
RN-004
20007
CONFIDENTIAL | [5 empty] | 2020-12-22
CCN-004
Project: | CTC
CCN-004 | Coordination of Existing Mall Condition/Mall Roof Projection
Quotation Summary
DESCRIPTION |  | Quantity | Unit | $/Unit | COST | TOTAL
1 | Harris Quote |  |  |  | 2691.8 | 2691.8
2 | Synergy Quote |  |  |  | -2500 | -2500
3
4
5
6
7
SUBTOTAL | [5 empty] | 191.8
| Lundy's Mark-up 5% |  |  |  |  | 9.59
TOTAL | [5 empty] | 201.39
Lundy Concrete Quotation Breakdown
DESCRIPTION |  | Quantity | Unit | $/Unit | COST | TOTAL
1 |  |  |  |  | 0 | 0
2
3
4
5
6
7
TOTAL | [5 empty] | 0
There will be no change in the presently approved contract completion date due to this change
in the work; all costs to maintain this date are included in this CCO.
There will be a change to the present contract completion date of TBD days,
due to the changes in the work.
There may be a revision to the presently approved contract completion date; due to the changes
in the work. MPL reserves the right to assess the actual effects to the original completion date
at a later date due to the impact of this additional work.

## CCN-003R1
RN-003
20007
CONFIDENTIAL | [5 empty] | 2020-12-22
CCN-003R1
Project: | CTC
CCN-003R1 | Suit SD Markups, Site Conditions & RFIs
Quotation Summary
DESCRIPTION |  | Quantity | Unit | $/Unit | COST | TOTAL
1 | Thyssenkrupp Quote |  |  |  | 2760 | 2760
2 | Synergy Quote |  |  |  | 230 | 230
3 | Harris Quote |  |  |  | 2945.5 | 2945.5
4 | Simcon Quote |  |  |  | 14628 | 14628
5 | GA Masonry Quote |  |  |  |  | 0
6
7
SUBTOTAL | [5 empty] | 20563.5
| Lundy's Mark-up 5% |  |  |  |  | 1028.175
TOTAL | [5 empty] | 21591.675
Lundy Concrete Quotation Breakdown
DESCRIPTION |  | Quantity | Unit | $/Unit | COST | TOTAL
1 |  |  |  |  | 0 | 0
2
3
4
5
6
7
TOTAL | [5 empty] | 0
There will be no change in the presently approved contract completion date due to this change
in the work; all costs to maintain this date are included in this CCO.
There will be a change to the present contract completion date of TBD days,
due to the changes in the work.
There may be a revision to the presently approved contract completion date; due to the changes
in the work. MPL reserves the right to assess the actual effects to the original completion date
at a later date due to the impact of this additional work.

## CCN-002
RN-002
20007
CONFIDENTIAL | [5 empty] | 2020-12-22
CCN-002
Project: | CTC
CCN-002 | Structural Site Report No. 01
Quotation Summary
DESCRIPTION |  | Quantity | Unit | $/Unit | COST | TOTAL
1 | Simcon Quote |  |  |  | 6370 | 6370
2 | Harris Quote |  |  |  | -1444.95 | -1444.95
3 | Synergy Quote |  |  |  | 2984.25 | 2984.25
4 | Lundy Concrete Quote |  |  |  | 2547.74 | 2547.74
5
6
7
SUBTOTAL | [5 empty] | 10457.04
| Lundy's Mark-up 5% |  |  |  |  | 522.852
TOTAL | [5 empty] | 10979.892
Lundy Concrete Quotation Breakdown
DESCRIPTION |  | Quantity | Unit | $/Unit | COST | TOTAL
1 | Footing Concrete Volume - net increase | 13.9 | m3 | 139.65 | 1941.135 | 1941.135
2 | Slab on Grade Concrete Volume- net increase | 4 | m3 | 151.65 | 606.6 | 606.6
3
4
5
6
7
TOTAL | [5 empty] | 2547.735
There will be no change in the presently approved contract completion date due to this change
in the work; all costs to maintain this date are included in this CCO.
There will be a change to the present contract completion date of TBD days,
due to the changes in the work.
There may be a revision to the presently approved contract completion date; due to the changes
in the work. MPL reserves the right to assess the actual effects to the original completion date
at a later date due to the impact of this additional work.